## Sheet1
Additional class topic | [14 empty] | Intro Class |  |  |  |  | Design Process, SolidCAM Training |  | Design for Molding |  |  |  |  | Urethane Casting Demo |  | TBD |  |  |  |  | TBD |  | TL-1 CAM Training |  |  |  |  | TBD |  | TBD |  |  |  |  | TBD |  | Injection Molder Demo |  |  |  |  | TBD |  | TBD |  |  |  |  | TBD |  | TBD |  |  |  |  | No Class |  | No Class |  |  |  |  | Carbon fiber part design |  | Carbon Demo |  |  |  |  | Final Project PDR |  | TBD / Work time |  |  |  |  | Final Project Status Update 1 |  | TBD / Work time |  |  |  |  | Final Project Status Update 2 |  | TBD / Work time |  |  |  |  | Final Project CDR |  | TBD / Work time |  |  |  |  | Final Project Status Update 3 |  | TBD / Work time |  |  |  |  | Final Project Demo |  | TBD / Work time |  | Final Project Demo (actual)
Month / project due dates | Total Time | Days | Color | January | [9 empty] | Classes start | Candy Assigned |  |  |  | MLK day - no classes | MiniMill PDR, Mold Introduced, Vice stop due |  | Mini Mill CDR, CAM Reviews begin, mold PDR, Vise stop reflection due |  |  |  |  | Mold Urethane CDR | [5 empty] | Course selection period ends | Candy Due, Check Assigned | February | Check PDR, Candy reflection due |  |  |  |  | Mold Urethane Due, Check CDR, McMaster Order Due 8PM, TL-1 training starts |  | IM Assigned, Mold UC reflection due | [6 empty] | IM PDR | Drop period ends |  |  |  | IM CDR |  | Check Due |  |  |  |  | Check reflection due | March |  |  | Spring Break | Spring Break | Spring Break | Spring Break | Spring Break | Spring Break | Spring Break | Spring Break | Spring Break |  | Carbon Assigned |  | Carbon PDR, IM Due, Final project assigned |  |  |  |  | Mold IM Reflection due |  |  | Last day to withdraw from a course |  |  |  | Final Project Teams and Proposals Due |  | Analyze Due, Carbon Due |  | April |  |  | Analyze and Carbon reflection due | [21 empty] | Last day of classes
Date |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Day |  |  |  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Trial | 0 | 38 |  | Candy Assigned 12 T: 0; Candy Assigned 13 F: 0; Candy Assigned 14 S: 0; Candy Assigned 15 S: 0; MLK day - no classes 16 M: 0; MiniMill PDR, Mold Introduced, Vice stop due 17 T: 0
Vise Stop | 2 | 6 |  | Candy Assigned 12 T: 0.33333; Candy Assigned 13 F: 0.33333; Candy Assigned 14 S: 0.33333; Candy Assigned 15 S: 0.33333; MLK day - no classes 16 M: 0.33333; MiniMill PDR, Mold Introduced, Vice stop due 17 T: 0.33333
Mini Mill
Design | 15 | 8 |  | Candy Assigned 12 T: 1.875; Candy Assigned 13 F: 1.875; Candy Assigned 14 S: 1.875; Candy Assigned 15 S: 1.875; MLK day - no classes 16 M: 1.875; MiniMill PDR, Mold Introduced, Vice stop due 17 T: 1.875; MiniMill PDR, Mold Introduced, Vice stop due 18 W: 1.875; Mini Mill CDR, CAM Reviews begin, mold PDR, Vise stop reflection due 19 T: 1.875
Build | 8 | 15 |  | MiniMill PDR, Mold Introduced, Vice stop due 17 T: 0.53333; MiniMill PDR, Mold Introduced, Vice stop due 18 W: 0.53333; Mini Mill CDR, CAM Reviews begin, mold PDR, Vise stop reflection due 19 T: 0.53333; Mini Mill CDR, CAM Reviews begin, mold PDR, Vise stop reflection due 20 F: 0.53333; Mini Mill CDR, CAM Reviews begin, mold PDR, Vise stop reflection due 21 S: 0.53333; Mini Mill CDR, CAM Reviews begin, mold PDR, Vise stop reflection due 22 S: 0.53333; Mini Mill CDR, CAM Reviews begin, mold PDR, Vise stop reflection due 23 M: 0.53333; Mold Urethane CDR 24 T: 0.53333; Mold Urethane CDR 25 W: 0.53333; Mold Urethane CDR 26 T: 0.53333; Mold Urethane CDR 27 F: 0.53333; Mold Urethane CDR 28 S: 0.53333; Mold Urethane CDR 29 S: 0.53333; Course selection period ends 30 M: 0.53333; Candy Due, Check Assigned 31 T: 0.53333
Mold
Urethane Design | 8 | 8 | bar: MiniMill PDR, Mold Introduced, Vice stop due 17 T to Mold Urethane CDR 24 T
Urethane Build | 15 | 15 | bar: Mold Urethane CDR 24 T to Mold Urethane Due, Check CDR, McMaster Order Due 8PM, TL-1 training starts 7 T
Injection Design | 6 | 15 |  | IM Assigned, Mold UC reflection due 9 T: 0.4; IM Assigned, Mold UC reflection due 10 F: 0.4; IM Assigned, Mold UC reflection due 11 S: 0.4; IM Assigned, Mold UC reflection due 12 S: 0.4; IM Assigned, Mold UC reflection due 13 M: 0.4; IM Assigned, Mold UC reflection due 14 T: 0.4; IM Assigned, Mold UC reflection due 15 W: 0.4; IM PDR 16 T: 0.4; Drop period ends 17 F: 0.4; Drop period ends 18 S: 0.4; Drop period ends 19 S: 0.4; Drop period ends 20 M: 0.4; IM CDR 21 T: 0.4; IM CDR 22 W: 0.4; Check Due 23 T: 0.4
Injection Build | 15 | 15 | bar: IM CDR 21 T to Carbon PDR, IM Due, Final project assigned 16 T
Check
Design | 10 | 10 | bar: Candy Due, Check Assigned 31 T to IM Assigned, Mold UC reflection due 9 T
Build | 15 | 15 | bar: Mold Urethane Due, Check CDR, McMaster Order Due 8PM, TL-1 training starts 7 T to Check Due 23 T
Carbon
Build | 5 | 17 |  | Carbon Assigned 14 T: 0.29412; Carbon Assigned 15 W: 0.29412; Carbon PDR, IM Due, Final project assigned 16 T: 0.29412; Carbon PDR, IM Due, Final project assigned 17 F: 0.29412; Carbon PDR, IM Due, Final project assigned 18 S: 0.29412; Carbon PDR, IM Due, Final project assigned 19 S: 0.29412; Carbon PDR, IM Due, Final project assigned 20 M: 0.29412; Mold IM Reflection due 21 T: 0.29412; Mold IM Reflection due 22 W: 0.29412; Mold IM Reflection due 23 T: 0.29412; Last day to withdraw from a course 24 F: 0.29412; Last day to withdraw from a course 25 S: 0.29412; Last day to withdraw from a course 26 S: 0.29412; Last day to withdraw from a course 27 M: 0.29412; Final Project Teams and Proposals Due 28 T: 0.29412; Final Project Teams and Proposals Due 29 W: 0.29412; Analyze Due, Carbon Due 30 T: 0.29412
Analyze
Design | 10 | 17 |  | Carbon Assigned 14 T: 0.58824; Carbon Assigned 15 W: 0.58824; Carbon PDR, IM Due, Final project assigned 16 T: 0.58824; Carbon PDR, IM Due, Final project assigned 17 F: 0.58824; Carbon PDR, IM Due, Final project assigned 18 S: 0.58824; Carbon PDR, IM Due, Final project assigned 19 S: 0.58824; Carbon PDR, IM Due, Final project assigned 20 M: 0.58824; Mold IM Reflection due 21 T: 0.58824; Mold IM Reflection due 22 W: 0.58824; Mold IM Reflection due 23 T: 0.58824; Last day to withdraw from a course 24 F: 0.58824; Last day to withdraw from a course 25 S: 0.58824; Last day to withdraw from a course 26 S: 0.58824; Last day to withdraw from a course 27 M: 0.58824; Final Project Teams and Proposals Due 28 T: 0.58824; Final Project Teams and Proposals Due 29 W: 0.58824; Analyze Due, Carbon Due 30 T: 0.58824
Final
Design | 40 | 43 |  | Carbon PDR, IM Due, Final project assigned 16 T: 0.93023; Carbon PDR, IM Due, Final project assigned 17 F: 0.93023; Carbon PDR, IM Due, Final project assigned 18 S: 0.93023; Carbon PDR, IM Due, Final project assigned 19 S: 0.93023; Carbon PDR, IM Due, Final project assigned 20 M: 0.93023; Mold IM Reflection due 21 T: 0.93023; Mold IM Reflection due 22 W: 0.93023; Mold IM Reflection due 23 T: 0.93023; Last day to withdraw from a course 24 F: 0.93023; Last day to withdraw from a course 25 S: 0.93023; Last day to withdraw from a course 26 S: 0.93023; Last day to withdraw from a course 27 M: 0.93023; Final Project Teams and Proposals Due 28 T: 0.93023; Final Project Teams and Proposals Due 29 W: 0.93023; Analyze Due, Carbon Due 30 T: 0.93023; Analyze Due, Carbon Due 31 F: 0.93023; April 1 S: 0.93023; April 2 S: 0.93023; April 3 M: 0.93023; Analyze and Carbon reflection due 4 T: 0.93023; Analyze and Carbon reflection due 5 W: 0.93023; Analyze and Carbon reflection due 6 T: 0.93023; Analyze and Carbon reflection due 7 F: 0.93023; Analyze and Carbon reflection due 8 S: 0.93023; Analyze and Carbon reflection due 9 S: 0.93023; Analyze and Carbon reflection due 10 M: 0.93023; Analyze and Carbon reflection due 11 T: 0.93023; Analyze and Carbon reflection due 12 W: 0.93023; Analyze and Carbon reflection due 13 T: 0.93023; Analyze and Carbon reflection due 14 F: 0.93023; Analyze and Carbon reflection due 15 S: 0.93023; Analyze and Carbon reflection due 16 S: 0.93023; Analyze and Carbon reflection due 17 M: 0.93023; Analyze and Carbon reflection due 18 T: 0.93023; Analyze and Carbon reflection due 19 W: 0.93023; Analyze and Carbon reflection due 20 T: 0.93023; Analyze and Carbon reflection due 21 F: 0.93023; Analyze and Carbon reflection due 22 S: 0.93023; Analyze and Carbon reflection due 23 S: 0.93023; Analyze and Carbon reflection due 24 M: 0.93023; Analyze and Carbon reflection due 25 T: 0.93023; Last day of classes 26 W: 0.93023; Last day of classes 27 T: 0.93023
Build | 40 | 43 |  | Carbon PDR, IM Due, Final project assigned 16 T: 0.93023; Carbon PDR, IM Due, Final project assigned 17 F: 0.93023; Carbon PDR, IM Due, Final project assigned 18 S: 0.93023; Carbon PDR, IM Due, Final project assigned 19 S: 0.93023; Carbon PDR, IM Due, Final project assigned 20 M: 0.93023; Mold IM Reflection due 21 T: 0.93023; Mold IM Reflection due 22 W: 0.93023; Mold IM Reflection due 23 T: 0.93023; Last day to withdraw from a course 24 F: 0.93023; Last day to withdraw from a course 25 S: 0.93023; Last day to withdraw from a course 26 S: 0.93023; Last day to withdraw from a course 27 M: 0.93023; Final Project Teams and Proposals Due 28 T: 0.93023; Final Project Teams and Proposals Due 29 W: 0.93023; Analyze Due, Carbon Due 30 T: 0.93023; Analyze Due, Carbon Due 31 F: 0.93023; April 1 S: 0.93023; April 2 S: 0.93023; April 3 M: 0.93023; Analyze and Carbon reflection due 4 T: 0.93023; Analyze and Carbon reflection due 5 W: 0.93023; Analyze and Carbon reflection due 6 T: 0.93023; Analyze and Carbon reflection due 7 F: 0.93023; Analyze and Carbon reflection due 8 S: 0.93023; Analyze and Carbon reflection due 9 S: 0.93023; Analyze and Carbon reflection due 10 M: 0.93023; Analyze and Carbon reflection due 11 T: 0.93023; Analyze and Carbon reflection due 12 W: 0.93023; Analyze and Carbon reflection due 13 T: 0.93023; Analyze and Carbon reflection due 14 F: 0.93023; Analyze and Carbon reflection due 15 S: 0.93023; Analyze and Carbon reflection due 16 S: 0.93023; Analyze and Carbon reflection due 17 M: 0.93023; Analyze and Carbon reflection due 18 T: 0.93023; Analyze and Carbon reflection due 19 W: 0.93023; Analyze and Carbon reflection due 20 T: 0.93023; Analyze and Carbon reflection due 21 F: 0.93023; Analyze and Carbon reflection due 22 S: 0.93023; Analyze and Carbon reflection due 23 S: 0.93023; Analyze and Carbon reflection due 24 M: 0.93023; Analyze and Carbon reflection due 25 T: 0.93023; Last day of classes 26 W: 0.93023; Last day of classes 27 T: 0.93023
TOTAL | 189 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 3.7417 | 3.4083 | 3.4083 | 1.5333 | 1.5333 | 1.5333 | 1.5333 | 2.5333 | 1.5333 | 1.5333 | 1.5333 | 1.5333 | 1.5333 | 1.5333 | 2.5333 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 2.4 | 1.4 | 1.4 | 1.4 | 1.4 | 1.4 | 1.4 | 1.4 | 1.4 | 1.4 | 1.4 | 1.4 | 2.4 | 2.4 | 2.4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.8824 | 1.8824 | 3.7428 | 2.7428 | 2.7428 | 2.7428 | 2.7428 | 2.7428 | 2.7428 | 2.7428 | 2.7428 | 2.7428 | 2.7428 | 2.7428 | 2.7428 | 2.7428 | 2.7428 | 1.8605 | 1.8605 | 1.8605 | 1.8605 | 1.8605 | 1.8605 | 1.8605 | 1.8605 | 1.8605 | 1.8605 | 1.8605 | 1.8605 | 1.8605 | 1.8605 | 1.8605 | 1.8605 | 1.8605 | 1.8605 | 1.8605 | 1.8605 | 1.8605 | 1.8605 | 1.8605 | 1.8605 | 1.8605 | 1.8605 | 1.8605 | 1.8605
Aedhan Out | bar: Mold Urethane CDR 25 W to IM Assigned, Mold UC reflection due 15 W